## PERMIT REGISTER
NANA BAMBI'S PLACE — PERMIT, LICENCE & REGISTRATION CALENDAR
MASTER PERMIT REGISTER
All permits, licences, registrations, and certifications — Ragay, Camarines Sur
REF | PERMIT / LICENCE / REGISTRATION | ISSUING AUTHORITY | SPOKE / AREA | RESPONSIBLE | FREQUENCY | EST. COST (₱) | NEXT DUE | STATUS | NOTES
BR-001 | DTI Business Name Registration | DTI | All spokes | Aileen | 5-year | 500 | Sep 2031 | ACTIVE | Register before trading. Renewal every 5 years.
BR-002 | Mayor's Business Permit | LGU Ragay Municipal Hall | All spokes | Aileen | Annual (Jan) | 5,000 | Jan 2027 | PENDING | Apply within first month of operation. Renew every January.
BR-003 | Barangay Business Clearance | Barangay F. Simeon | All spokes | Aileen | Annual (Jan) | 200 | Jan 2027 | PENDING | Required before Mayor's Permit. Get this first.
BR-004 | BIR Certificate of Registration (COR) | BIR RDO Naga | All spokes | Aileen / Grace | Once + annual | 500 | Jan 2027 (annual) | PENDING | Register before first transaction. All invoices must use BIR-registered receipts from day 1.
BR-005 | BIR Books of Accounts | BIR RDO Naga | All spokes | Grace | Annual (April) | 200 | Apr 2027 | PENDING | Books stamped annually at BIR.
BR-006 | Sanitary Permit | Municipal Health Office Ragay | All spokes | Aileen | Annual (Jan) | 1,000 | Jan 2027 | PENDING | Required for all food-handling operations.
BR-007 | Fire Safety Clearance / Inspection | Bureau of Fire Protection Ragay | All spokes | Aido | Annual (Jan) | 1,500 | Jan 2027 | PENDING | Required for all business operations.
BR-008 | Zoning Clearance / Land Use | Municipal Planning Office Ragay | Hub | Aileen | Once | 1,000 | Sep 2026 | PENDING | Confirm agricultural-commercial zoning for hub site.
BR-009 | BMBE Registration | DTI / LGU | All spokes | Aileen | 3-year | 500 | 2029 | ASSESS | If total assets under ₱3M — income tax exemption. Confirm eligibility with accountant.
FS-001 | FDA Licence to Operate — Food (Panaderia/Café) | FDA Philippines | Panaderia / Café | Aileen | Annual | 3,000 | Jan 2027 | PENDING | Required before selling bread, processed foods. Apply at FDA CAR / Region V.
FS-002 | FDA Licence to Operate — Cold Chain / Meat | FDA Philippines | Butcher / Deliveries | Aileen | Annual | 5,000 | Jan 2027 | PENDING | Required for meat processing and cold chain operations.
FS-003 | NMIS Meat Establishment Accreditation | NMIS Region V | Butcher | Aileen | Annual | 3,000 | Jan 2027 | PENDING | Required for butcher counter. GMP and SSOP manuals must be in place first.
FS-004 | HACCP Certification (Butcher / Cold Chain) | NMIS / FDA | Butcher / Deliveries | Aido | Annual | 10,000 | Jan 2027 | ASSESS | Required for AAA-rated establishments. Lawyer to advise if mandatory for your scale.
FS-005 | Meat Transport Vehicle (MTV) Accreditation — Local | LGU Veterinarian Ragay | Deliveries | Jim | Annual | 1,000 | Jan 2027 | PENDING | Required before any meat is transported. Per vehicle. LGU vet accredits local delivery.
FS-006 | Meat Transport Vehicle (MTV) Accreditation — Inter-provincial | NMIS Region V | Deliveries | Jim | Annual | 2,000 | Jan 2027 | ASSESS | Required if delivering meat across provincial boundaries (Ragay to Quezon). Lawyer to advise.
FS-007 | Cold Chain Integrity Docket System | Internal / NMIS | Deliveries | Jim / Grace | Ongoing | 0 | Ongoing | ACTIVE | Temperature log at dispatch and delivery. No docket = no cold chain delivery. Already in SOP.
FS-008 | PhilGAP Certification — Produce | DA Region V | Regen Gardening / Nursery | Aileen | Annual | 2,000 | 2027 | ASSESS | Good Agricultural Practices certification for produce. Lawyer / DA to advise.
LV-001 | DA-BAI Poultry Farm Registration | Bureau of Animal Industry (BAI) Region V | Poultry | Aileen | Annual | 1,000 | Jan 2027 | PENDING | Register Agrupacion poultry farm with BAI before first flock. Annual renewal.
LV-002 | DA Livestock Farm Registration | DA Region V | Livestock | Aileen | Annual | 1,000 | Jan 2027 | PENDING | Register livestock operation with DA.
LV-003 | BAI Livestock Handler Licence | BAI Region V | Livestock | Jim | Annual | 300 | Jan 2027 | PENDING | Required for anyone handling and moving livestock. Jim must have this.
LV-004 | BAI Transport Carrier Accreditation (livestock) | BAI Region V | Deliveries | Jim | Annual — per vehicle | 500 | Jan 2027 | PENDING | Per vehicle used for livestock transport. Annual renewal requires seminar attendance.
LV-005 | BAI Livestock Shipping Permit | BAI Region V | Livestock | Jim | Per shipment (7-day validity) | 200 | Per use | PENDING | One permit per shipment, per vehicle, per destination. Valid 7 days only. Jim to know this process cold.
LV-006 | Veterinary Health Certificate (livestock) | Municipal Veterinarian Ragay | Livestock | Aileen | Annual + per movement | 500 | Jan 2027 | PENDING | Annual certificate plus per-movement VHC. Coordinate with Municipal Vet Ragay.
LV-007 | DA-PRDP Slaughterhouse Arrangement (Agrupacion) | LGU Ragay / Benedict Almario | Butcher | Aileen | Annual MOU renewal | 0 | Sep 2026 | PENDING | Formalise the arrangement with Benedict. Proposal letter sent. Follow up on arrival.
LV-008 | PCIC Livestock Insurance | PCIC via DA Region V | Livestock / Poultry | Aileen | Annual | Varies | Jan 2027 | ASSESS | Government-subsidised crop and livestock insurance. Investigate via local DA office.
MR-001 | BFAR Fish Buying Station Permit | BFAR Region V Pili | Marine & Seafood | Aileen | Annual | 3,000 | Jan 2027 | PENDING | Cannot commercially buy fish without this. Apply BFAR Region V before first fish purchase.
MR-002 | BFAR Fish Transport Permit | BFAR Region V | Marine & Seafood | Jim | Per shipment | 500 | Per use | PENDING | Required for transporting fish across municipal boundaries.
MR-003 | Local Government Fish Landing Clearance | LGU Ragay / Barangay | Marine & Seafood | Aileen | Annual | 500 | Jan 2027 | ASSESS | Coordinate with LGU for barangay fish landing point clearance.
VH-001 | LTO Registration — Isuzu NPS 4x4 (FL-001) | LTO Naga | Deliveries | Jim | Annual (Oct) | 5,000 | Oct 2027 | PENDING | First purchase on arrival. Register day of acquisition.
VH-002 | LTO Registration — Nana Bambi's Jeepney (FL-002) | LTO Naga | Deliveries | Jim | Annual (Oct) | 3,000 | Oct 2027 | PENDING | Register as commercial vehicle. FL-002.
VH-003 | LTO Registration — Additional Fleet Vehicles | LTO Naga | Deliveries | Jim | Annual (Oct) | 3,000–5,000 | Oct 2027 | PENDING | FL-003 onwards — register same day as each vehicle acquired.
VH-004 | CTPL Insurance — All Vehicles | LTO-accredited insurer | All Fleet | Jim | Annual (with LTO) | 1,500/vehicle | Oct 2027 | PENDING | Compulsory third party liability. Required for LTO registration.
VH-005 | Comprehensive Insurance — Commercial Vehicles | MAPFRE / Malayan / Cebuana | All Fleet | Jim | Annual | 8,000–15,000/vehicle | Oct 2027 | PENDING | Commercial vehicle comprehensive cover. Get quotes from 3 insurers.
VH-006 | Driver's Licence — Kuya Jim (Professional) | LTO Naga | Deliveries | Jim | 5-year | 1,000 | 2031 | ACTIVE | Professional driver's licence. Confirm current licence is valid and professional grade.
VH-007 | Driving NC III (TESDA) — Kuya Jim | TESDA RTC Pili / RPSI Ragay | Deliveries | Jim | Once | 14,000 (company-paid) | 2026 | PENDING | TESDA study allowance ₱14,000 included in Jim's contract. Enrol on arrival.
VH-008 | LTFRB Franchise — Delivery For-Hire | LTFRB Region V | Deliveries | Aileen / Lawyer | Once | 5,000 | ASSESS | ASSESS | Required if carrying goods for hire beyond own business. Lawyer to advise if applicable.
EN-001 | DENR Environmental Compliance Certificate | DENR Region V | Hub / Farm | Aileen / Lawyer | Once (project) | Varies | ASSESS | ASSESS | Required for certain construction. Lawyer to advise if full ECC or CoNC applies.
EN-002 | Water Use Permit — Surface Water | NWRB / DENR | Hub / Aquaponics | Aileen / Lawyer | 5-year | 2,000 | ASSESS | ASSESS | Required for commercial water abstraction. Lawyer to advise.
EN-003 | Waste Management Compliance | DENR / LGU | Hub / Butcher | Aileen | Annual | 500 | Jan 2027 | PENDING | Solid waste management plan and compliance with RA 9003.
EN-004 | Wastewater Discharge Permit | DENR EMB Region V | Hub / Butcher | Aileen / Lawyer | Annual | 3,000 | ASSESS | ASSESS | Required if discharging wastewater. Lawyer to advise.
CN-001 | Building Permit — Manager's Residence | LGU Ragay Engineering Office | Hub | Aido | Once (per structure) | Varies | Sep 2026 | PENDING | Required before construction. Based on floor area and assessed value.
CN-002 | Building Permit — Hub Structure (Stage 2) | LGU Ragay Engineering Office | Hub | Aido | Once (per structure) | Varies | 2027 | PENDING | Stage 2 CHB structure — permit required before pour.
CN-003 | Building Permit — Playground / Undercover Roof | LGU Ragay / Barangay | Community Space | Aido | Once | 2,000 | 2027 | PENDING | GI sheet undercover roof requires building permit. Playground = basic barangay permit.
CN-004 | Occupancy Permit — All Structures | LGU Ragay Engineering Office | Hub | Aido | Once (per structure) | Varies | After build | PENDING | Required after construction is complete before occupancy.
CN-005 | Electrical Permit / Inspection | LGU / CASURECO | Hub | Aido | Once + annual | 1,000 | Sep 2026 | PENDING | Electrical inspection required before energisation.
LB-001 | SSS Employer Registration | SSS | All staff | Grace | Once | 0 | Sep 2026 | PENDING | Register as employer before first payroll.
LB-002 | PhilHealth Employer Registration | PhilHealth | All staff | Grace | Once | 0 | Sep 2026 | PENDING | Register as employer before first payroll.
LB-003 | Pag-IBIG Employer Registration | Pag-IBIG | All staff | Grace | Once | 0 | Sep 2026 | PENDING | Register as employer before first payroll.
LB-004 | DOLE Business Registration / BWSC Report | DOLE Region V | All staff | Aileen | Annual (Jan) | 0 | Jan 2027 | PENDING | Annual report to DOLE on employees, wages, and working conditions.
LB-005 | Employees Compensation (EC) Registration | ECC | All staff | Grace | Once | 0 | Sep 2026 | PENDING | Automatic with SSS employer registration.
IM-001 | 13A Visa — Aido (Spouse of Filipino Citizen) | BI Philippines | Personal — Aido | Aido / Aileen | Annual then Permanent | 8,500 | Sep 2026 | PENDING | Apply on arrival. Balikbayan privilege covers first 12 months. 13A gives work rights.
IM-002 | ACR I-Card (Alien Certificate of Registration) | BI Philippines | Personal — Aido | Aido | Annual then 5-year | 4,000 | Sep 2026 | PENDING | Required alongside 13A. Apply at same time.
IM-003 | Re-entry Permit (if leaving Philippines) | BI Philippines | Personal — Aido | Aido | Per trip | 1,000 | As needed | ASSESS | Required if leaving and returning on 13A status.
SA-001 | Mayor's Permit — Each Satellite LGU | Respective LGU (Sipocot/Daet/Tagkawayan) | Satellite Stores | Aileen | Annual (Jan) per LGU | 5,000 each | Jan 2027 | ASSESS | Each LGU where you operate a satellite store or fixed delivery point requires its own Mayor's Permit. Ragay permit covers nothing outside Ragay.
SA-002 | Barangay Clearance — Each Satellite Location | Respective Barangay | Satellite Stores | Aileen | Annual per location | 200 each | Jan 2027 | ASSESS | One per satellite barangay location.
SA-003 | Sanitary Permit — Each Satellite | Respective Municipal Health Office | Satellite Stores | Aileen | Annual per location | 1,000 each | Jan 2027 | ASSESS | Required at each satellite food-handling location.
SA-004 | Fire Clearance — Each Satellite | BFP per municipality | Satellite Stores | Aileen | Annual per location | 1,500 each | Jan 2027 | ASSESS | Required at each permanent satellite location.

## URGENT NOW
NANA BAMBI'S PLACE — PERMIT, LICENCE & REGISTRATION CALENDAR
URGENT NOW — Before Trading Begins
These permits must be in place before September 2026 arrival or before any spoke opens
REF | PERMIT | CATEGORY | SPOKE | RESPONSIBLE | DEADLINE | EST. COST | ACTION REQUIRED | STATUS
BR-004 | BIR Certificate of Registration | Business | All | Aileen | Before first transaction | ₱500 | Register with BIR RDO Naga before first sale. Non-negotiable. All invoices need BIR receipts from day 1. | CRITICAL
BR-002 | Mayor's Business Permit | Business | All | Aileen | On arrival Sep 2026 | ₱5,000 | Apply at Ragay Municipal Hall immediately on arrival. Required to operate. | CRITICAL
BR-003 | Barangay Business Clearance | Business | All | Aileen | On arrival Sep 2026 | ₱200 | Get this before Mayor's Permit — it's a prerequisite. | CRITICAL
LB-001 | SSS Employer Registration | Labour | All staff | Grace | Before first payroll | ₱0 | Register before hiring anyone. SSS contributions from Day 1 — no exceptions. | CRITICAL
LB-002 | PhilHealth Employer Registration | Labour | All staff | Grace | Before first payroll | ₱0 | Same as SSS — Day 1. | CRITICAL
LB-003 | Pag-IBIG Employer Registration | Labour | All staff | Grace | Before first payroll | ₱0 | Same as SSS — Day 1. | CRITICAL
IM-001 | 13A Visa — Aido | Immigration | Personal | Aido / Aileen | On arrival Sep 2026 | ₱8,500 | Apply at Bureau of Immigration on arrival. Balikbayan covers first 12 months but apply immediately. | CRITICAL
IM-002 | ACR I-Card — Aido | Immigration | Personal | Aido | On arrival Sep 2026 | ₱4,000 | Apply alongside 13A. | CRITICAL
CN-001 | Building Permit — Residence | Construction | Hub | Aido | Before construction | Varies | Apply at LGU Engineering before first pour. | PENDING
BR-006 | Sanitary Permit | Business | All food | Aileen | Before food sales | ₱1,000 | Required before any food is sold. | PENDING
BR-007 | Fire Safety Clearance | Business | All | Aido | Before opening | ₱1,500 | BFP inspection required before trading. | PENDING
LV-001 | BAI Poultry Farm Registration | Livestock | Poultry | Aileen | Before first flock | ₱1,000 | Register Agrupacion farm with BAI before any birds arrive. | PENDING
LV-007 | DA-PRDP Slaughterhouse MOU | Livestock | Butcher | Aileen | On arrival Sep 2026 | ₱0 | Follow up with Benedict Almario — proposal letter already sent. | PENDING
FS-001 | FDA Licence to Operate — Food | Food Safety | Panaderia/Café | Aileen | Before food sales | ₱3,000 | Apply FDA Region V before selling bread or café food. | PENDING
VH-001 | LTO Registration — FL-001 Isuzu | Vehicle | Deliveries | Jim | Day of purchase | ₱5,000 | Register vehicle same day invoice is paid. | PENDING
MR-001 | BFAR Fish Buying Station Permit | Marine | Marine | Aileen | Before first fish purchase | ₱3,000 | Cannot buy fish commercially without this. | PENDING
DL-001 | MTV Accreditation — Meat Transport | Food Safety | Deliveries | Jim | Before meat delivery | ₱1,000 | LGU vet accreditation for any vehicle carrying meat. | PENDING

## 5-YEAR CALENDAR
NANA BAMBI'S PLACE — PERMIT, LICENCE & REGISTRATION CALENDAR
5-YEAR RENEWAL CALENDAR 2026–2031
When each permit falls due — plan your cash flow and Grace's workload
REF | PERMIT | FREQUENCY | 2026 | 2027 | 2028 | 2029 | 2030 | 2031
BR-001 | DTI Business Name | 5-year | Sep 2026 |  |  |  |  | Sep 2031
BR-002 | Mayor's Permit | Annual | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
BR-003 | Barangay Clearance | Annual | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
BR-004 | BIR COR | Annual (Apr) | Sep 2026 | Apr 2027 | Apr 2028 | Apr 2029 | Apr 2030 | Apr 2031
BR-006 | Sanitary Permit | Annual (Jan) | Sep 2026 | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
BR-007 | Fire Safety Clearance | Annual (Jan) | Sep 2026 | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
FS-001 | FDA LTO — Food | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
FS-002 | FDA LTO — Cold Chain/Meat | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
FS-003 | NMIS Meat Establishment | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
FS-005 | MTV Accreditation (local) | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
LV-001 | BAI Poultry Farm Reg | Annual (Jan) | Sep 2026 | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
LV-002 | DA Livestock Farm Reg | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
LV-003 | BAI Handler Licence | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
LV-004 | BAI Transport Carrier | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
MR-001 | BFAR Fish Buying Station | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
VH-001 | LTO FL-001 Isuzu | Annual (Oct) | Oct 2026 | Oct 2027 | Oct 2028 | Oct 2029 | Oct 2030 | Oct 2031
VH-002 | LTO FL-002 Jeepney | Annual (Oct) | Oct 2026 | Oct 2027 | Oct 2028 | Oct 2029 | Oct 2030 | Oct 2031
VH-004 | CTPL Insurance (all fleet) | Annual (Oct) | Oct 2026 | Oct 2027 | Oct 2028 | Oct 2029 | Oct 2030 | Oct 2031
VH-005 | Comprehensive Insurance | Annual (Oct) | Oct 2026 | Oct 2027 | Oct 2028 | Oct 2029 | Oct 2030 | Oct 2031
VH-006 | Driver's Licence — Jim | 5-year | [5 empty] | 2031
VH-007 | TESDA Driving NC III — Jim | Once | 2026
LB-001 | SSS Employer Reg | Once | Sep 2026
LB-002 | PhilHealth Employer Reg | Once | Sep 2026
LB-003 | Pag-IBIG Employer Reg | Once | Sep 2026
LB-004 | DOLE BWSC Report | Annual (Jan) |  | Jan 2027 | Jan 2028 | Jan 2029 | Jan 2030 | Jan 2031
IM-001 | 13A Visa — Aido | Annual→Permanent | Sep 2026 | Sep 2027
IM-002 | ACR I-Card — Aido | Annual→5yr | Sep 2026 | Sep 2027 |  |  |  | Sep 2031
CN-001 | Building Permit — Residence | Once | Sep 2026
CN-002 | Building Permit — Hub Stage 2 | Once |  | 2027
EN-001 | DENR ECC (if required) | Once (ASSESS) | ASSESS

## BY PERSON
NANA BAMBI'S PLACE — PERMIT, LICENCE & REGISTRATION CALENDAR
BY RESPONSIBLE PERSON
Who owns what — accountability by name
PERSON | REF | PERMIT | FREQUENCY | NEXT DUE | STATUS | NOTES
AILEEN
| BR-001 | DTI Business Name Registration | 5-year | Sep 2031 | ACTIVE | Register before trading. Renewal every 5 years.
| BR-002 | Mayor's Business Permit | Annual (Jan) | Jan 2027 | PENDING | Apply within first month of operation. Renew every January.
| BR-003 | Barangay Business Clearance | Annual (Jan) | Jan 2027 | PENDING | Required before Mayor's Permit. Get this first.
| BR-004 | BIR Certificate of Registration (COR) | Once + annual | Jan 2027 (annual) | PENDING | Register before first transaction. All invoices must use BIR-registered receipts from day 1.
| BR-006 | Sanitary Permit | Annual (Jan) | Jan 2027 | PENDING | Required for all food-handling operations.
| BR-008 | Zoning Clearance / Land Use | Once | Sep 2026 | PENDING | Confirm agricultural-commercial zoning for hub site.
| BR-009 | BMBE Registration | 3-year | 2029 | ASSESS | If total assets under ₱3M — income tax exemption. Confirm eligibility with accountant.
| FS-001 | FDA Licence to Operate — Food (Panaderia/Café) | Annual | Jan 2027 | PENDING | Required before selling bread, processed foods. Apply at FDA CAR / Region V.
| FS-002 | FDA Licence to Operate — Cold Chain / Meat | Annual | Jan 2027 | PENDING | Required for meat processing and cold chain operations.
| FS-003 | NMIS Meat Establishment Accreditation | Annual | Jan 2027 | PENDING | Required for butcher counter. GMP and SSOP manuals must be in place first.
| FS-008 | PhilGAP Certification — Produce | Annual | 2027 | ASSESS | Good Agricultural Practices certification for produce. Lawyer / DA to advise.
| LV-001 | DA-BAI Poultry Farm Registration | Annual | Jan 2027 | PENDING | Register Agrupacion poultry farm with BAI before first flock. Annual renewal.
| LV-002 | DA Livestock Farm Registration | Annual | Jan 2027 | PENDING | Register livestock operation with DA.
| LV-006 | Veterinary Health Certificate (livestock) | Annual + per movement | Jan 2027 | PENDING | Annual certificate plus per-movement VHC. Coordinate with Municipal Vet Ragay.
| LV-007 | DA-PRDP Slaughterhouse Arrangement (Agrupacion) | Annual MOU renewal | Sep 2026 | PENDING | Formalise the arrangement with Benedict. Proposal letter sent. Follow up on arrival.
| LV-008 | PCIC Livestock Insurance | Annual | Jan 2027 | ASSESS | Government-subsidised crop and livestock insurance. Investigate via local DA office.
| MR-001 | BFAR Fish Buying Station Permit | Annual | Jan 2027 | PENDING | Cannot commercially buy fish without this. Apply BFAR Region V before first fish purchase.
| MR-003 | Local Government Fish Landing Clearance | Annual | Jan 2027 | ASSESS | Coordinate with LGU for barangay fish landing point clearance.
| VH-008 | LTFRB Franchise — Delivery For-Hire | Once | ASSESS | ASSESS | Required if carrying goods for hire beyond own business. Lawyer to advise if applicable.
| EN-001 | DENR Environmental Compliance Certificate | Once (project) | ASSESS | ASSESS | Required for certain construction. Lawyer to advise if full ECC or CoNC applies.
| EN-002 | Water Use Permit — Surface Water | 5-year | ASSESS | ASSESS | Required for commercial water abstraction. Lawyer to advise.
| EN-003 | Waste Management Compliance | Annual | Jan 2027 | PENDING | Solid waste management plan and compliance with RA 9003.
| EN-004 | Wastewater Discharge Permit | Annual | ASSESS | ASSESS | Required if discharging wastewater. Lawyer to advise.
| LB-004 | DOLE Business Registration / BWSC Report | Annual (Jan) | Jan 2027 | PENDING | Annual report to DOLE on employees, wages, and working conditions.
| IM-001 | 13A Visa — Aido (Spouse of Filipino Citizen) | Annual then Permanent | Sep 2026 | PENDING | Apply on arrival. Balikbayan privilege covers first 12 months. 13A gives work rights.
| SA-001 | Mayor's Permit — Each Satellite LGU | Annual (Jan) per LGU | Jan 2027 | ASSESS | Each LGU where you operate a satellite store or fixed delivery point requires its own Mayor's Permit. Ragay permit covers nothing outside Ragay.
| SA-002 | Barangay Clearance — Each Satellite Location | Annual per location | Jan 2027 | ASSESS | One per satellite barangay location.
| SA-003 | Sanitary Permit — Each Satellite | Annual per location | Jan 2027 | ASSESS | Required at each satellite food-handling location.
| SA-004 | Fire Clearance — Each Satellite | Annual per location | Jan 2027 | ASSESS | Required at each permanent satellite location.
AIDO
| BR-007 | Fire Safety Clearance / Inspection | Annual (Jan) | Jan 2027 | PENDING | Required for all business operations.
| FS-004 | HACCP Certification (Butcher / Cold Chain) | Annual | Jan 2027 | ASSESS | Required for AAA-rated establishments. Lawyer to advise if mandatory for your scale.
| CN-001 | Building Permit — Manager's Residence | Once (per structure) | Sep 2026 | PENDING | Required before construction. Based on floor area and assessed value.
| CN-002 | Building Permit — Hub Structure (Stage 2) | Once (per structure) | 2027 | PENDING | Stage 2 CHB structure — permit required before pour.
| CN-003 | Building Permit — Playground / Undercover Roof | Once | 2027 | PENDING | GI sheet undercover roof requires building permit. Playground = basic barangay permit.
| CN-004 | Occupancy Permit — All Structures | Once (per structure) | After build | PENDING | Required after construction is complete before occupancy.
| CN-005 | Electrical Permit / Inspection | Once + annual | Sep 2026 | PENDING | Electrical inspection required before energisation.
| IM-001 | 13A Visa — Aido (Spouse of Filipino Citizen) | Annual then Permanent | Sep 2026 | PENDING | Apply on arrival. Balikbayan privilege covers first 12 months. 13A gives work rights.
| IM-002 | ACR I-Card (Alien Certificate of Registration) | Annual then 5-year | Sep 2026 | PENDING | Required alongside 13A. Apply at same time.
| IM-003 | Re-entry Permit (if leaving Philippines) | Per trip | As needed | ASSESS | Required if leaving and returning on 13A status.
GRACE
| BR-004 | BIR Certificate of Registration (COR) | Once + annual | Jan 2027 (annual) | PENDING | Register before first transaction. All invoices must use BIR-registered receipts from day 1.
| BR-005 | BIR Books of Accounts | Annual (April) | Apr 2027 | PENDING | Books stamped annually at BIR.
| FS-007 | Cold Chain Integrity Docket System | Ongoing | Ongoing | ACTIVE | Temperature log at dispatch and delivery. No docket = no cold chain delivery. Already in SOP.
| LB-001 | SSS Employer Registration | Once | Sep 2026 | PENDING | Register as employer before first payroll.
| LB-002 | PhilHealth Employer Registration | Once | Sep 2026 | PENDING | Register as employer before first payroll.
| LB-003 | Pag-IBIG Employer Registration | Once | Sep 2026 | PENDING | Register as employer before first payroll.
| LB-005 | Employees Compensation (EC) Registration | Once | Sep 2026 | PENDING | Automatic with SSS employer registration.
JIM (Kuya Jim)
| FS-005 | Meat Transport Vehicle (MTV) Accreditation — Local | Annual | Jan 2027 | PENDING | Required before any meat is transported. Per vehicle. LGU vet accredits local delivery.
| FS-006 | Meat Transport Vehicle (MTV) Accreditation — Inter-provincial | Annual | Jan 2027 | ASSESS | Required if delivering meat across provincial boundaries (Ragay to Quezon). Lawyer to advise.
| FS-007 | Cold Chain Integrity Docket System | Ongoing | Ongoing | ACTIVE | Temperature log at dispatch and delivery. No docket = no cold chain delivery. Already in SOP.
| LV-003 | BAI Livestock Handler Licence | Annual | Jan 2027 | PENDING | Required for anyone handling and moving livestock. Jim must have this.
| LV-004 | BAI Transport Carrier Accreditation (livestock) | Annual — per vehicle | Jan 2027 | PENDING | Per vehicle used for livestock transport. Annual renewal requires seminar attendance.
| LV-005 | BAI Livestock Shipping Permit | Per shipment (7-day validity) | Per use | PENDING | One permit per shipment, per vehicle, per destination. Valid 7 days only. Jim to know this process cold.
| MR-002 | BFAR Fish Transport Permit | Per shipment | Per use | PENDING | Required for transporting fish across municipal boundaries.
| VH-001 | LTO Registration — Isuzu NPS 4x4 (FL-001) | Annual (Oct) | Oct 2027 | PENDING | First purchase on arrival. Register day of acquisition.
| VH-002 | LTO Registration — Nana Bambi's Jeepney (FL-002) | Annual (Oct) | Oct 2027 | PENDING | Register as commercial vehicle. FL-002.
| VH-003 | LTO Registration — Additional Fleet Vehicles | Annual (Oct) | Oct 2027 | PENDING | FL-003 onwards — register same day as each vehicle acquired.
| VH-004 | CTPL Insurance — All Vehicles | Annual (with LTO) | Oct 2027 | PENDING | Compulsory third party liability. Required for LTO registration.
| VH-005 | Comprehensive Insurance — Commercial Vehicles | Annual | Oct 2027 | PENDING | Commercial vehicle comprehensive cover. Get quotes from 3 insurers.
| VH-006 | Driver's Licence — Kuya Jim (Professional) | 5-year | 2031 | ACTIVE | Professional driver's licence. Confirm current licence is valid and professional grade.
| VH-007 | Driving NC III (TESDA) — Kuya Jim | Once | 2026 | PENDING | TESDA study allowance ₱14,000 included in Jim's contract. Enrol on arrival.

## LEGEND & CONTACTS
NANA BAMBI'S PLACE — PERMIT, LICENCE & REGISTRATION CALENDAR
LEGEND, CONTACTS & CRITICAL NOTES
Reference sheet — keep this open. Grace and Jim to read before first renewal.
STATUS KEY
CRITICAL | Must be done immediately — operation cannot start without this
PENDING | Action required — apply before spoke opens
ACTIVE | In place and current
ASSESS | Check with lawyer/accountant — may or may not be required
KEY REGULATORY CONTACTS
BIR RDO Naga | Naga City — all tax registration and compliance
LGU Ragay / Municipal Hall | Business permits, building permits, zoning — Ragay Poblacion
Benedict Almario | Municipal Agriculturist Ragay — DA contact, slaughterhouse, PCIC
BAI Region V | Bureau of Animal Industry — Pili, Camarines Sur. Poultry/livestock permits
BFAR Region V | Bureau of Fisheries — Pili. Fish buying station permit
FDA Region V | Food and Drug Administration — Naga. LTO food and cold chain
NMIS Region V | National Meat Inspection Service — meat establishment accreditation
DENR Region V | Environmental compliance — Naga
DOLE Region V | Labour compliance — Naga
LTO Naga / Pili | Vehicle registration — Gencars Naga for Isuzu dealer
BI (Bureau of Immigration) | Manila or Naga satellite — 13A visa and ACR I-Card for Aido
TESDA RTC Pili / RPSI Ragay | Jim's Driving NC III enrolment
CRITICAL RULES — READ THESE
JANUARY is deadline month | Mayor's Permit, Barangay Clearance, Sanitary Permit, Fire Clearance, FDA LTO, DA/BAI permits, DOLE — nearly all annual permits renew in January. Start 30 days before = December 1.
OCTOBER is fleet month | All LTO registrations and vehicle insurance fall due in October. Budget ₱3,000–₱5,000 per vehicle plus insurance.
BAI Shipping Permit = 7 days only | One permit, one vehicle, one destination, one shipment. Valid 7 days only. Jim must apply before EVERY livestock movement.
Satellite LGUs = separate permits | Ragay Mayor's Permit covers nothing outside Ragay. Every LGU where a satellite store or fixed delivery point operates needs its own full permit set.
Cold chain docket = mandatory | Every licensed cold chain delivery requires a signed docket. Temperature logged at dispatch and arrival. No docket = dry delivery rate, customer notified.
Asset register = same day | Every asset (vehicle, equipment) must be entered in the register the same day the invoice is paid. No exceptions.
All invoices = BIR receipts | From Day 1, every transaction must use BIR-registered official receipts. No unofficial receipts. Grace is accountable for this.
ASSESS items — lawyer first | Any permit marked ASSESS must be reviewed with the Naga lawyer before deciding whether to apply. Do not skip ASSESS items — some carry significant penalties.